## Intro
System Design Assessment
This tool provides metrics for assessing the quality of systems engineering and development environment.
This assessment tool is based on Metrics and Case Studies for Evaluating Engineering Designs by: J. A. Moody, W. L. Chapman, F. D. Van Voorhees and A. T. Bahill, Prentice Hall PTR, 1997. The assessment model is used with permission of A. T. Bahill. This book is out of print but used copies are available. The model has been updated based on material in The Mechanical Design Process 6th edition.
On the spreadsheets, material in The Mechanical Design Process 6th edition is referenced by "MDP". The spreadsheets were developed by Prof. David G. Ullman. An example is available for the Northrop B-2 Stealth Bomber.
The method can be used to assess systems engineering projects using five broad categories as shown in the table below. There is one worksheet for each of the categories. The scores are automatically updated in this table as the sheets are filled in. The categories are divided into two broad areas: 1) Difficulty and Resources are best applied to completed projects whereas; 2) Performance, Engineering and Environment can be applied to new or past projects.
Importance weightings can be applied to the measures in Performance, Engineering and Environment and not to Difficulty and Resources. This is because the Difficulty and Resources are inherent in the project itself, whereas there is control in the other areas. This becomes clear during the assessment.
Enter the name of the system being assessed here. Name will propagate other sheets.
Scores automatically updated as you fill in the other sheets.
System Name:
Total System Scores
| Engineering | 50 | Note that all scores in this table are normalized to 100 (perfect). This was not done in the original book.
| Environment | 50
| Performance | 50
| Difficulty | 32
| Resources | 17

## Engineering
Systems Engineering Fundamentals
System Name:
Enter importance weightings in the yellow boxes using the pull-downs. Importance weightings range from 1 (unimportant) to 10 (very important).
Assess your project by entering scores in the pink boxes using pull-down of potential values.
The system will compute total in the green boxes.
Systems Engineering Fundamentals measures the use of systems engineering best practices. These measures identify the top-level key principles, activities and tasks that should be considered during any development program.
|  | Importance | Score | Total
Requirements Development (See MDP Chapter 6) |  | 1 | 5 | 5 | 1
Scoring Guide | Measures the accuracy and thoroughness of understanding and documenting the customers' problems and needs. |  |  |  | 2
| 7-10 - Accurate and thorough understanding and documentation of the customers' problems and needs. |  |  |  | 3
| 4-6 - Reasonably accurate understanding and documentation of the customers' problems and needs. |  |  |  | 4
| 0-3 - Inadequate understanding and documentation of the customers' problems and needs. |  |  |  | 5
System Understanding (See MDP Section7.2) |  | 1 | 5 | 5 | 6
Scoring Guide | Measures the extent to which the functional decomposition is performed based on performance objectives and understanding the system constraints and interfaces |  |  |  | 7
| 7-10 - Well refined function and interface understanding addressed before concept development. |  |  |  | 8
| 4-6 - Reasonable function and interface understanding develop prior to concept development. |  |  |  | 9
| 0-3 - Inadequate function and interface understanding. |  |  |  | 10
Concept Development (See MDP Chapters 7 and 8) |  | 1 | 5 | 5
Scoring Guide | Measures the effort made to evaluate alternative concepts using a formal or informal design tradeoff methodology
7-10 - Thorough consideration and analysis of alternative systems and concepts using formal or informal design trade-off methods.
4-6 - Reasonable consideration and analysis of alternative systems and concepts using formal or informal design trade-off methods.
0-3 -Little or no consideration and analysis of alternative systems and concepts using formal or informal design trade-off methods.
Make/Buy Decisions (See Template 20: MakeBuy) |  | 1 | 5 | 5
Scoring Guide | This measures the quality of the decisions made about whether or to build or buy components, assemblies or sub-systems. These need not consume much time, but should be made in a rational and documented manner considering in-house capabilities.
7-10 - Good quality Make/Buy decisions.
4-6 - Many Make/Buy decisions made by default with no formal effort.
0-3 - Little or no Make/Buy decision making.
Validation (See MDP Chapter 10) |  | 1 | 5 | 5
Scoring Guide | Measures how well the established requirements are consistent with the customer needs and that a real-world solution can be built and tested to prove that it satisfies those requirements.
7-10 - A methodical process is used involving direct interaction with the customer.
4-6 - A process is used that is indirect such as referencing market surveys.
0-3 - Little or no effort for revising requirements with regard to the customer.
Verification and testing (See MDP Chapter 10) |  | 1 | 5 | 5
Scoring Guide | Measures the degree to which the design and as-built hardware and software complies with performance specifications.
9-10 - The use of a comprehensive test plan to confirm that the hardware and software comply with the specifications and drawings.
3-4 - A partial job of testing compliance.
0-2 - A poor job of compliance.
Configuration Management (See MDP Section 12.4) |  | 1 | 5 | 5
Scoring Guide | This measures the degree to which there is a "single truth" and any changes are traceable and managed with a formal system.
9-10 - Changes are controlled and a single truth maintained.
3-4 - A fair job is done maintaining a single truth.
0-2 - There is no single truth and changes are poorly managed.
Manufacturing Considerations (See MDP Sections 11.2 and 11.3) |  | 1 | 5 | 5
Scoring Guide | Manufacturing decisions are made concurrently with design decisions with the configuration sensitive to the cost and ease of fabrication (Design for Manufacture) and assembly (Design for Assembly).
9-10 -
3-4 - 21% to 50% overdue
0-2 - More than 51% overdue
Systems Integration (See MDP Sections 2.3, 5.3 and 8.6) |  | 1 | 5 | 5
Scoring Guide | Measures how well the sub-systems interact to meet the customers' needs. This includes organizing the technical effort, integrating the activities of the development teams, resolving design conflicts and assessing and managing technical risk.
7-10 - Sub-system are brought together through a well-organized and integrated technical effort the balances the influence of all required design specialties.
4-6 - Brings sub-systems together with significant difficulty
0-3 - Fails to bring the sub-systems together effectively
Life-cycle considerations (See MDP Sections 4.4, 11.5, 11.6, and 11.7) |  | 1 | 5 | 5
Scoring Guide | Giving priority to long term issues such as supportability and life cycle costs.
7-10 - Fully recognizes and addresses supportability and life-cycle cost requirements early in development.
4-6 - Recognizes and minimally addresses supportability and life-cycle costs early in development
0-3 - Supportability and life-cycle costs are not adequately addressed early in development.
Program Management (See MDP Chapter 5) |  | 1 | 5 | 5
Scoring Guide | Measures how well the planning, tracking, and coordination of activities is performed by all elements of the development team.
7-10 - A strong program management function that effectively keeps the effort on track through the use of an accurate integrated master scheduling system.
4-6 - A moderate program management function that keeps the effort mostly on track.
0-3 - A poor program management function on track.
|  |  | Total Engineering Score | 55
|  | Normalized to 100 |  | 50
11

## Environment
Design Environment
System Name:
Enter importance weightings in the yellow boxes using the pull-downs. Importance weightings range from 1 (unimportant) to 10 (very important).
Assess your project by entering scores in the pink boxes using pull-down of potential values.
The system will compute total in the green boxes.
Measures the environment in which the systems are developed. It can as important as the other factors. Some of these measures are under the control of the design team and others are not.
|  |  | Importance | Score | Total
| Emphasis on the Customer (See MDP Chapter 6) |  | 1 | 5 | 5
| Scoring Guide | The customer requirements are the primary design drivers. Continuous customer input throughout the development process is essential.
|  | 7-10 - High emphasis on receiving and positively responding to direct and indirect customer development. |  |  |  | 1
|  | 4-6 - Moderate emphasis on receiving and positively responding to direct and indirect customer development. |  |  |  | 2
|  | 0-3 - Little or no emphasis on receiving and positively responding to direct and indirect customer development. |  |  |  | 3
| Stability of Requirements and Configuration |  | 1 | 5 | 5 | 4
| Scoring Guide | Requirement changes need to be carefully managed. In the ideal world, there would be no changes during the project but this is unreal. Poor change management can lead to an endless project with no hope of finishing because the target keeps moving. |  |  |  | 5
|  | 7-10 - Minor changes to or no changes in customers' requirements. |  |  |  | 6
|  | 4-6 - Reasonable changes to customers' requiremnts and they are controled and documented. |  |  |  | 7
|  | 0-3 - Major changes to customers requirements. |  |  |  | 8
| Funding and Workforce Level Stability |  | 1 | 5 | 5 | 9
| Scoring Guide | Measures the constancy of funding and people. Projects that start and stop or have a change in personnel have historically been less successful than those who are stable. |  |  |  | 10
7-10 - No un-planned, major changes in funding or workforce levels and management.
4-6 - Few un-planned, major changes in funding or workforce levels and management.
0-3 -Major un-planned, major changes in funding or workforce levels and management.
| Project Support |  | 1 | 5 | 5
| Scoring Guide | Measures the level of support within the company
7-10 - Strong support throughout he development process with no significant controversy threatening the viability of the project.
4-6 - Moderate or uneven support throughout he development process due to controversy that threatens the viability of the project.
0-3 -Low support throughout he development process with the viability of the project in doubt.
| Continuity of Core Development Team |  | 1 | 5 | 5
| Scoring Guide | Measures the degree to which the core teams of designers and the managers remain throughout development with minimal turnover of personnel.
7-10 - Little or no turnover of key people.
4-6 - Some turnover of key people.
0-3 - High turnover of key people.
| Stability of Organizational Structure |  | 1 | 5 | 5
| Scoring Guide | Measures the degree to which the system development organization goes through major reorganizations during the project.
7-10 - The organization is stable
4-6 - The is some reorganization during the project
0-3 - The project is extensively reorganized
| Cooperation Amongst Stakeholders |  | 1 | 5 | 5
| Scoring Guide | Measure the existence of positive, non confrontational working relationships among the team members and team members and customers.
7-10 - Good cooperation
4-6 - Moderate cooperation
0-2 - Low cooperation
| Effective Communication |  | 1 | 5 | 5
| Scoring Guide | Measures how well the design teams, sub-contractors and customers communicate and coordinate amongst themselves. Good communication is evidenced by the existence and use of good communication tools and platforms.
7-10 - Very good communication
4-6 - Moderate communication
0-3 - Weak communication
| Flexibility and Autonomy |  | 1 | 5 | 5
| Scoring Guide | Measures the ability to implement design changes quickly, not hampered by organizational or procedural roadblocks and without bureaucratic micromanagement.
7-10 - Very flexible with team responsible for change decisions
4-6 - Moderately flexible and autonomous
0-3 - Bound by bureaucracy and micromanagement
| Work Force Qualifications |  | 1 | 5 | 5
| Scoring Guide | Development personnel have appropriate education and experience to successfully develop the system,
7-10 - Completely
4-6 - Partially
0-3 - Poorly
| Accountability for System Performance |  | 1 | 5 | 5
| Scoring Guide | Accountability and authority are aligned so that the system developers can be help accountable to the customer for the resulting system's performance .
7-10 - Good accountability
4-6 - Moderate accountability
0-3 - Weak accountability
|  | Total Environment Score |  |  | 55
|  |  | Normalized to 100 |  | 50

## Performance
Performance
System Name:
Enter importance weightings in the yellow boxes using the pull-downs. Importance weightings range from 1 (unimportant) to 10 (very important).
Assess your project by entering scores in the pink boxes using pull-down of potential values.
The system will compute total in the green boxes.
The Performance assessment measures the degree of success of the overall development process for the system.
|  |  | Importance | Score | Total
| Technical Performance Initial (See MDP Chapter 10) |  | 1 | 5 | 5 | 0
| Scoring Guide | Measures compliance with the customers' performance requirements. How well the system achieves key technical performance requirements. |  |  |  | 1
|  | 7-10 - Highly successful system: The customer is highly satisfied. |  |  |  | 2
|  | 4-6 - Moderately successful system: . The customer is moderately satisfied. |  |  |  | 3
|  | 0-3 - Unsuccessful system: Low customer satisfaction. |  |  |  | 4
| Technical Performance Mature (See MDP Chapter 10) |  | 1 | 5 | 5 | 5
| Scoring Guide | Measures compliance with the customers' performance requirements one or two years after delivery. How well the system achieves key technical performance requirements. |  |  |  | 6
|  | 7-10 - Highly successful system: The customer is highly satisfied. |  |  |  | 7
|  | 4-6 - Moderately successful system: . The customer is moderately satisfied. |  |  |  | 8
|  | 0-3 - Unsuccessful system: Low customer satisfaction. |  |  |  | 4
| Cost Performance (See MDP Section 11.2) |  | 1 | 5 | 5 | 5
| Scoring Guide | Measures compliance with the budget. |  |  |  | 6
|  | 9-10 - Below budget or within 5% of baseline cost estimate |  |  |  | 7
|  | 7-8 - A 6% to 15% cost overrun |  |  |  | 8
|  | 5-6 - A 16% to 35% cost overrun |  |  |  | 9
|  | 3-4 - A 36% to 75% cost overrun |  |  |  | 10
|  | 0-2 - More than 75% cost growth |  |  |  | 11
| Schedule Performance (See MDP Section 5.4) |  | 1 | 5 | 5 | 12
| Scoring Guide | Measures the percentage of time that the effort is overdue. |  |  |  | 13
|  | 9-10 - Less than 2% overdue |  |  |  | 14
|  | 7-8 - 3% to 10%overdue |  |  |  | 15
5-6 - 11% to 20% overdue
3-4 - 21% to 50% overdue
0-2 - More than 51% overdue
|  |  |  | Total Performance Score | 20
|  |  | Normalized to 100 |  | 50
1

## Difficulty
Design Difficulty
System Name:
|  | Measures the technical challenges faced in developing the system. | Score
| Technology Readiness (see MDP Section 8.4) |  | 7 | 0
| Scoring Guide | Measures how much original thought goes into the project. Assessment should be based on the most challenging technologies in the system. |  | 1
|  | 15 - New to the world. This project requires invention or discovery of new concepts that have not been applied before. |  | 2
|  | 10-14 - New to this team. There are examples but no one on the team has used the key technologies before. Requires some innovation. |  | 3
|  | 4-9 - Some experience with the technologies, but this is a new application. Requires little innovation. |  | 4
|  | 0-3 - Requires little innovation as the technologies are known and ready for use. |  | 5
| Team Readiness (see MDP Section 3.7) |  | 5 | 6
| Scoring Guide | Measures the number and availability of the people with the necessary knowledge to do the project. |  | 7
|  | 7-10 - The team is fully staffed with people knowledgeable about the technologies used in the system. |  | 8
|  | 4-6 - The team has access to others outside the team for needed knowledge and experience. |  | 9
|  | 0-3 -the team lacks key people with knowledge and experience. |  | 10
| Complexity (See MDP Figure 3.12) |  | 5 | 11
| Scoring Guide | Measures the number of components needed in the system. Score = 2.5 * log (number of components) |  | 12
|  | 10 - More than 10,000 components. |  | 13
|  | 5 - Around 100 components |  | 14
|  | 0 - One component. |  | 15
| Product Quality (see MDP throughout) |  | 5
| Scoring Guide | Measures the desired quality of the system as seen in the development process. This begins with the inherent customers' expectation (see MDP Table 2.1) and is reflected through the use of QFD (see MDP Chapter 6) and other best practices such as concern for defect rate, reliability and maintainability (See MDP Sections 11.5 and 11.6)
7-10 - High emphasis on quality techniques.
4-6 - Moderate emphasis on system quality
0-3 -Little or no attention to quality related techniques.
| Manufacturing Process Design (See MDP Section 11.3 and 11.4) |  | 5
| Scoring Guide | Measures the complexity of the manufacture and assemble of the components to make up the system.
9-10 - Easy to make components and well thought out assembly processes. Designed to meet a large market
7-5 - Moderate complexity requiring custom tooling and set up
3-4 - Complex manufacturing for small quantities
0-2 - One-off system that is hand built.
| Aggressive Selling Price (See MDP Section 11.2) |  | 5
| Scoring Guide | Measures the degree to which the system is driven and constrained by unit sales price
9-10 - Very challenging sales price in a high competitive market
8-5 - Moderately challenging unit sales price
0-2 - Sales price is not very important
|  | Total Design Difficulty Score | 32
|  | Normalized to 100 | 49.2308

## Resources
Resources
System Name:
|  | This category measures the resources used to develop the system. It is primarily useful in retrospect. | Score
| Cost (MPD Section 11.2) |  | 7 | 0
| Scoring Guide | Measures the amount needed to pay for development, including salaries, utilities, supplies, and materials. |  | 1
|  | 14-15 - Massively expensive systems requiring major sacrifices. |  | 2
|  | 9-13 - Very expensive systems that are rarely developed. |  | 3
|  | 3-8 - Moderately expensive systems |  | 4
|  | 0-3 - Affordable systems. |  | 5
| Time (See MDP Sections 2.2.3 and 5.4.3) |  | 5 | 6
| Scoring Guide | Measures the time spent from the beginning of the effort to define the customer's needs through the first production unit. |  | 7
|  | 10 - More than eight years. |  | 8
|  | 8-9 - Five to eight years. |  | 9
|  | 4-7 - One to five years |  | 10
|  | 0-3 - Six months to one year. |  | 11
| Infrastructure |  | 5 | 12
| Scoring Guide | Measures the physical resources needed for constructions, transportation, communication, utilities, laws and legal protections, skilled management and education system available. |  | 13
|  | 9-10 - Massive infrastructure needed requiring major portions of the available labor force and equipment. |  | 14
|  | 6-8 - Complex infrastructures requiring large portions of the cost of the entire project. |  | 15
3-5 - Moderate infrastructure required.
0-2 -Common infrastructure.
|  | Total Resources Score | 17
|  | Normalized to 100 | 48.5714